GCSE Controlled Assessment Planner

| Week | Proposed Actions | Actual Actions |
| --- | --- | --- |
| 0 - Introduction | Identify a few possible problems to solve for the project. Research Diary |  |
| Session 1 2 hours 20 | Establish coursework aim. Discuss problems with supervisor and gain approval for project. |  |
|  | Carry out internet, book, magazine and catalogue research into chosen problem. Write up notes in Research Diary, listing all references used. |  |
| Session 2 2 hours 18 | Carry out at least one practical investigation into parameters for the specification for the artifact to be constructed. |  |
|  | Write up notes in Research Diary. Draw up formal specification for the artifact. It should include at least two numerical parameters. State specification in Research Diary. |  |
| Session 3 2 hours 16 | Discuss specification with supervisor - gain approval. Discuss system diagram with supervisor. Discuss alternatives - systems, subsystems etc. Investigate merits of each. |  |
|  | Write up notes in Research Diary of alternatives considered and why the chosen solution has been adopted. Draw system diagram in Research Diary. Devise the circuit diagram of the first subsystem to construct. Calculate a component value. |  |
| Session 4 2 hours 14 | Construct first subsystem and test that it works. Make measurements on it and assess its performance. |  |
|  | Write up details of first sub-system in Research Diary. Devise the circuit diagrams for the remaining subsystems. Ensure that all of the materials are available for the practical session. |  |

| Session 5 2 hours 12 | Construction of subsystems. |  |
| --- | --- | --- |
|  | Review progress of construction and note progress within Research Diary. |  |
| Session 6 2 hours 10 | Construction of subsystems. |  |
|  | Review progress of construction and note progress within Research Diary. |  |
| Session 7 2 hours 8 | Connect together all of the subsystems and persuade them to work together. |  |
|  | Devise test procedure for the performance parameters of the system and write up in Research Diary. |  |
| Session 8 2 hours 6 | Carry out measurements on the performance parameters of the system. Assess performance and identify any short comings. Start writing report from research diary. |  |
|  | Devise any modifications needed to improve the performance of the system. |  |
| Session 9 2 hours 4 | Carry out modifications. Re-measure performance parameters of the specification. Evaluate system against the initial specification. Continue writing up report from Research Diary. Photograph final system. Include Bibliography. |  |
| Session 10 2 hours 2 | Demonstrate working system to supervisor. Review report with supervisor. Make final changes to report. Hand in report. Celebrate! |  |